## Sheet1
Project Name |  | Fibi Implementation | Departments can request pre-reviews from specified reviewers before routing to the Research Administration Office for approval.
Script Name |  | UAT 2.12 Review (Pre-review)
Test Completion Date
Testor(s)
| Task Description | Steps to Execute | Expected Results | Pass | Fail | Comments
Fibi
1 | Find a partner to work with in this session via chat. | Via chat find a partner or ask Bob, Ellen, Emily or Angel to assist. |  |  |  | Partner Name:
2 | Open a PD - In Progress and Navigate to the Review tab | Login to Fibi - https://trfibi.johnshopkins.edu/fibi/#/login USe your JHEDID and the password: polus12
3 | 2.12.1 Create a Review request | Click on Proposal tab > Choose a PD in Progress from the list or create a PD > Click on Review tab | Review tab should open.
4 |  | Choose any Review Type from the dropdown menu.
5 |  | Enter the Reviewer, your partner from step 1, you wish to review your question(s) in the Reviewer field. Enter the individual’s last name and a dropdown will begin to populate.
6 |  | Enter a question(s) in the Comment box.
7 |  | Click on Add Request button. | You should see the request down below and your partner should see the Request for Review on the their Action List.
8 | 2.12.2 Verify the notification in the Action List widget | Click on the Dashboard icon > Find Action List > Click on the Review request from your partner > Click on Review tab | PD should open.
9 | 2.12.3 Respond to the Request - Write a Review | Click on Write a review > Enter text in Comment box > Click on Add Review button | Comments should show on the screen below with date and time stamp. Status shoes as In Progress.
10 | 2.12.4 Return to Applicant - Reject | Click on Return to Applicant button> Enter comments > Click on Return to Applicant | Comments should show on the screen below with date and time stamp. Status changes to Revision Requested.
11 | 2.12.5 Complete Review | Create a New Review request with your partner - see steps 3-7. Click on Complete Review button> Enter comments > Click on Complete Review button | Comments should show on the screen below with date and time stamp and Review is marked as Complete. |  |  | PD#
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30