## Sheet1
Project Name |  | Fibi Implementation
Script Name |  | UAT 2.9 - Attachments
Test Completion Date
Testor(s)
| Task Description | Steps to Execute | Expected Results | Pass | Fail | Comments
Fibi
1 | Navigate to the Proposal Module | Login to Fibi > Click on Proposal tab.
2 | Search for a proposal of your choosing | Choose a Proposal from My Proposals or Create a New Proposal.
3 | Open the proposal | Click on the Proposal row desired. |  |  |  | Note Proposal # here
4 | 2.9.1.1 Proposal Attachments Add 5 or more attachments all at once with drag option | Click on the Attachments tab > Click on the + Add attachments button under Proposal Attachments> Click and drag a group of documents from your desktop and drop them in the box that reads Drop your files here. >Select attachment type from the dropdown menu > Click on Add button. | 1. Attachments should show with updated by information in the record. 2. Attachments should show on Proposal tab of the record as well.
5 | 2.9.1.2 Proposal Attachments Add 5 or more attachments all at once with choose files option | Click on the + Add attachments button under Proposal Attachments> Click on Choose files link > Click on a file > Hold down the Shift key and click on the last file desired in the group of files listed > Click Open button > Select attachment type from the dropdown menu > Click on Add button. | 1. Attachments should show with updated by information in the record. 2. Attachments should show on Proposal tab of the record as well.
| 2.9.1.3 Personnel Attachments Add 5 or more attachments all at once with drag option | Click on the + Add attachments button under Personnel Attachment section> Click and drag a group of documents from your desktop and drop them in the box that reads Drop your files here. > Choose a person from the dropdown to associate the document > Select attachment type from the dropdown menu > Click on Add button.
| 2.9.1.4 Personnel Attachments Add 5 or more attachments all at once with choose files option | Click on the + Add attachments button under Personnel Attachments> Click on Choose files link > Click on a file > Hold down the Shift key and click on the last file desired in the group of files listed > Click Open button > Choose a person from the dropdown menu to associate the document > Select attachment type from the dropdown menu > Click on Add button.
6 | 2.9.2 Swap out a document for another document | Goto the list of attachments you just added and click on the replace icon (two arrows that make a rectangle)
7 | 2.9.2.1 Swap out a document for another document using the drag option | Click and drag a file from your desktop to the Drop your file here box > Click on Replace button. | 1. The file name should change approporiately. 2. Click on the Version icon (green document with refresh arrow, see below for icon) and you will see the previous version of the document.
8 | 2.9.2.2 Swap out a document for another document using the Choose File option. | Click on Choose files link > Click on a file > Click Open button > Click on Replace button. | 1. The file name should change approporiately. 2. Click on the Version icon (green document with refresh arrow, see below for icon) and you will see the previous version of the document.
9 | 2.9.3 Edit entries | Click on the edit icon (blue pencil) next to one of the attachments > change the attachment type from the dropdown > click on the update button | 1. The attachment type should change appropriately. 2. The attachment information should also change appropriately on the Proposal tab.
10 |  | Click on the edit icon (blue pencil) next to one of the attachments > change or add a description in the description box > click on the update button | 1. The description box should display with the changes/additions. 2. The description should change appropriately on the Proposal tab as well.
11 |  | Click on the edit icon (blue pencil) next to one of the attachments > change the status to final or draft from the status dropdown menu > click on the update button | 1. The status should change appropriately. 2. The status should change appropriately on the Proposal tab.
12 | 2.9.4 Route the proposal for review (or choose a Proposal with a Status - Approval in Progress that has attachments) | Click on Submit (upper right corner)
13 | Swap out a document for another document during routing | Goto the list of attachments you just added and click on the replace icon (two arrows that make a rectangle)
14 | 2.9.4.1 Swap out a document for another document during routing using the drag option | Click and drag a file from your desktop to the Drop your file here box > Click on Replace button. | 1. The file name should change approporiately. 2. Click on the Version icon (green document with refresh arrow, see below for icon) and you will see the previous version of the document.
15 | 2.9.4.2 Swap out a document for another document during routing using the Choose file option | Click on Choose files link > Click on a file > Click Open button > Click on Replace button. | 1. The file name should change approporiately. 2. Click on the Version icon (green document with refresh arrow, see below for icon) and you will see the previous version of the document.
Coeus
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20